## Slide 1
14.1 Project Management Introduction
Using UML, Patterns, and Java
Object-Oriented Software Engineering

## Slide 2: Can you develop this?
Notes: The answer to the question “Can we develop this” depends on what we mean by developing.
Let us assume, that we mean by “development” that it that it eventually can be used by an end user.
Can we develop this? No, if we ask an artist, he will say, yes. Because in this case the end user might be a connesseur of art, who puts a drawing of this on the wall in her living room.
There are a variety of famous artists who made their fortune with these types of drawing (Escher, Dali).
So, defining it to be “useful for an end user” is not enough.

## Slide 3: Software Production has a Poor Track Record Example: Space Shuttle Software
Cost: $10 Billion, millions of dollars more than planned
Time: 3 years late
Quality: First launch of Columbia was cancelled because of a synchronization problem with the Shuttle's 5 onboard computers.
  Error was traced back to a change made 2 years earlier when a programmer changed a delay factor in an interrupt handler from 50 to 80 milliseconds.
  The likelihood of the error was small enough, that the error caused no harm during thousands of hours of testing.
Substantial errors still exist.
  Astronauts are supplied with a book of known software problems "Program Notes and Waivers".

## Slide 4: …has major impact on Users

## Slide 5: Outline of today’s lecture
Basic definitions: Project, Project Plan, Project Agreement
Software Project Management Plan
  Project Organization
  Managerial Processes
  Technical Processes
  Work Packages
Building a House (Example to illustrate the concepts)
Work Breakdown Structures
Dependency Graphs
Tasks, Activities and Project Functions

## Slide 6: Basic Definitions: Project and Project Plan
Software Project:
  All technical and managerial activities required to deliver the deliverables to the client.
  A software project has a specific duration, consumes resources and produces work products.
  Management categories to complete a software project:
    Tasks, Activities, Functions
Software Project Management Plan:
  The controlling document for a software project.
  Specifies the technical and managerial approaches to develop the software product.
  Companion document to requirements analysis document:
    Changes in either document may imply changes in the other document.
  The SPMP may be part of the project agreement.
Notes: Tthe central notion of project management is the software project. It defines the technical and managerial activities to develop a product and deliver it to the client.
The central part of the managerial activities is the software project management plan.
A project consists of activities, tasks, and functions.

## Slide 7: Components of a Project

## Slide 8: A More Complex Model
Notes: During the lecture we will show you how this complex model can easily be understood and reconstructed (think of this as a modeling exercise in UML).

## Slide 9: States of a Project

## Slide 10: Project Agreement
Document written for a client that defines:
  the scope, duration, cost and deliverables for the project.
  the exact items, quantities, delivery dates, delivery location.
Client: Individual or organization that specifies the requirements and accepts the project deliverables.
Can be a contract, a statement of work, a business plan, or a project charter.
Deliverables (= Work Products that will be delivered to the client:
  Documents
  Demonstrations of function
  Demonstration of nonfunctional requirements
  Demonstrations of subsystems

## Slide 11: IEEE Std 1058: Standard for Software Project Management Plans (SPMP)
What it does:
  Specifies the format and contents of software project management plans.
  It provides a standard set of abstractions for a project manager or a whole organization to build its set of practices and procedures for developing software project management plans
  Abstractions: Project, Function, Activities, Tasks
What it does not do:
  It does not specify the procedures or techniques to be used in the development of the plan
  It does not provide examples .

## Slide 12: Project Agreement,Problem Statement vs SPMP

## Slide 13: Software Project Management Plan Template
0. Front Matter
1. Introduction
2. Project Organization
3. Managerial Process
4. Technical Process
5. Work Elements, Schedule, Budget
Optional Inclusions

## Slide 14: SPMP Part 0: Front Matter
Title Page
Revision sheet (update history)
Preface: Scope and purpose
Tables of contents, figures, tables

## Slide 15: SPMP Part 1: Introduction
1.1 Project Overview
  Executive summary: description of project, product summary
1.2 Project Deliverables
  All items to be delivered, including delivery dates and location
1.3 Evolution of the SPMP
  Plans for anticipated and unanticipated change
1.4 Reference Materials
  Complete list of materials referenced in SPMP
1.5 Definitions and Acronyms

## Slide 16: SPMP Part 2: Project Organization
2.1 Process Model
  Relationships among project elements
2.2 Organizational Structure
  Internal management, organization chart
2.3 Organizational Interfaces
  Relations with other entities (subcontractors, commercial software)
2.4 Project Responsibilities
  Major functions and activities; nature of each; who’s in charge
  Matrix of project functions/activities vs responsible individuals

## Slide 17: Organizational Structure Example

## Slide 18: SPMP Part 3: Managerial Process
3.1 Management Objectives and Priorities
  Describes management philosophy, priorities among requirements, schedule and budget
3.2 Assumptions, Dependencies and Constraints
  External events the project depends on, constraints under which the project is to be conducted
3.3 Risk Management
  Identification and assessment of risk factors, mechanism for tracking risks, implementation of contigency plans
3.5 Monitoring and Controlling Mechanisms
  Frequency and mechanisms for reporting
3.4 Staffing Plan
  Numbers and types of personnel required to conduct the project

## Slide 19: Examples of Risk Factors
Contractual risks
  What do you do if the client becomes bankrupt?
Size of the project
  What do you do if you feel the project is too large?
Complexity of the project
  What do you do if the requirements are multiplying during analysis? („requirements creep“)
Personal
  How do you hire people? Is there a danger of people leaving the project?
Client acceptance
  What do you do, if the client does not like the developed prototype?

## Slide 20: SPMP Part 4: Technical Process
2.1 Methods, Tools and Techniques
  Specify the methods, tools and techniques to be used on the project
2.2 Software Documentation
  Describe the documentation plan
2.3 Project Support Functions
  Plans for (at least) the following project support functions.
    Plan to ensure quality assurance
    Configuration management plan (IEEE Std 1042)
    Verification and validation plan
  The plans can be included in this section or there is a reference to a separate document

## Slide 21: SPMP Part 5: Description of Work Packages
Work Breakdown Structure (WBS) (Section 5.1)
  Hierarchical decomposition of the project into activities and tasks
Dependencies between tasks (Section 5.2)
  An important temporal relation: “must be preceded by”
  Dependency graphs show temporal dependencies of the activities:
Notes: Let's cover in a little bit more detail the work elements
First we begin by working to understand what the customer and users want. We list all the items that the customer expects to see during the development of the project. These items are called deliverables and can included anything the customer wants demonstrated or delivered as part of the project agreement.
Note that the Workbreakdown structure is very much like a to-do list. It is useful to use a word processor that allows an outline feature, or a project management tool to start with a to-do list. Listing all the to-dos and ordering them into a hierarchical relationship (Task A consists of the subtasks A1, A2, ...) is the first activity of producing a project plan.
The next step in the formulation of a project plan is to identify any dependencies between activities, tasks or functions. Note that dependency is another relation different from the “consists of” relation. Dependency is a relation between two tasks, activities or functions that denotes “must be preceded by”. If task A depends on another task B , in general it means that task B has to precede task A, otherwise task A cannot start or cannot get done.

## Slide 22: Work package vs Work product
Definitions from the IEEE Standard
Work Package:
  A specification for the work to be accomplished in an activity or task
Work Product:
  Any tangible item that results from a project function, activity or task.
Project Baseline:
  A work product that has been formally reviewed and agreed upon.
  A project baseline can only be changed through a formal change procedure
Project Deliverable:
  A work product to be delivered to the client

## Slide 23: How can we model a work product?
What is a tangible item?
  Requirements Analysis Document
  Software Project Management Plan
  Agenda, Minutes
  How do we model Tangible Items?

## Slide 25: Work products are related to Activities
How do we model this?

## Slide 26: Work Breakdown Structure
The hierarchical representation of all the tasks in a project is called the work breakdown structure (WBS). First Version of a UML Model
But Tasks are Parts of Activities. What would be a better model?

## Slide 27: Creating Work Breakdown Structures
Two major philosophies
  Activity-oriented decomposition („Functional decomposition“)
    Write the book
    Get it reviewed
    Do the suggested changes
    Get it published
  Result-oriented („Object-oriented decomposition“)
    Chapter 1
    Chapter 2
    Chapter 3
Which one is best for managing? Depends on project type:
  Development of a prototype
  Development of a product
  Project team consist of many unexperienced beginners
  Project team has many experienced developers

## Slide 28: Estimates for establishing WBS
Establishing an WBS in terms of percentage of total effort:
  Small project (7 person-month): at least 7% or 0.5 PM
  Medium project (300 person-month): at least 1% or 3 PMs
  Large project (7000 person-month): at least 0.2 % or 15 PMs
  (From Barry Boehm, Software Economics)

## Slide 29: Example: Let‘s Build a House
What are the activities that are needed to build a house?

## Slide 30: Typical activities when building a house
Surveying
Excavation
Request Permits
Buy Material
Lay foundation
Build Outside Wall
Install Exterior Plumbing
Install Exterior Electrical
Install Interior Plumbing
Install Interior Electrical
Install Wallboard
Paint Interior
Install Interior Doors
Install Floor
Install Roof
Install Exterior Doors
Paint Exterior
Install Exterior Siding
Buy Pizza
Finding these activities is a brainstorming activity.
It is requires similar activities used during analysis (use case modeling)

## Slide 31: Hierarchical organization of the activities
Building the house consists of
  Prepare the building site
  Building the Exterior
  Building the Interior
Preparing the building site consists of
  Surveying
  Excavation
  Buying of material
  Laying of the foundation
  Requesting permits

## Slide 32: Partial Work Breakdown Structure

## Slide 33: From the WBS to the Dependency Graph
The work breakdown structure does not show any temporal dependence among the activities/tasks
  Can we excavate before getting the permit?
  How much time does the whole project need if I know the individual times?
    What can be done in parallel?
  Are there any critical actitivites, that can slow down the project significantly?
Temporal dependencies are shown in the dependency graph
  Nodes are activities
  Lines represent temporal dependencies

## Slide 34: Building a House (Dependency Graph)
START
Request
Survey
ing
Excava
tion
Buy
Material
Founda
tion
Build
Outside
Wall
Install
Exterior
Plumbing
Install
Interior
Plumbing
Install
Exterior
Electrical
Install
Interior
Electrical
Install
Exterior
Siding
Install
Wallboard
Paint
Exterior
Install
Roofing
Install
Flooring
Paint
Interior
Install
Interior
Doors
Install
Exterior
Doors
FINISH
The activity
„Buy Material“ must
Precede the activity
„Lay foundation“
Lay

## Slide 35: SPMP Part 5: Description of Work Packages ctd
Resource Requirements (5.3)
  Estimates of the total resource (Personnel, Computer Time, Support Software) required to complete the project
  Numbers and types of personnel
  Computer time
  Office and laboratory facilities
  Travel
  Maintenance and training requirements
Budget (5.4)
Schedule (Section 5.5)
  Estimate the duration of each task
  Label dependency graph with the estimates

## Slide 36: Building a House (PERT Chart)
Duration
Start Time
Slack Time
Each Activity has a start time and an estimated duration
START
8/27/94
0
0
Request
Permits
8/27/94
15
0
Survey
ing
8/27/94
3
12
Excava
tion
9/17/94
10
0
Legend
8/29/94
0
Buy
Material
10/1/94
10
0
Lay
Founda
tion
10/15/94
15
0
Build
Outside
Wall
11/5/94
20
0
Install
Exterior
Plumbing
12/3/94
10
12
Install
Interior
Plumbing
12/3/94
12
0
Install
Exterior
Electrical
12/17/94
10
12
Install
Interior
Electrical
12/21/94
15
0
Install
Exterior
Siding
12/31/94
8
12
Install
Wallboard
1/11/95
9
0
Paint
Exterior
1/12/95
5
12
Install
Roofing
1/19/95
9
12
Install
Flooring
1/22/95
18
0
Paint
Interior
1/22/95
11
0
Install
Interior
Doors
2/8/95
7
0
Install
Exterior
Doors
1/19/95
6
15
FINISH
2/16/95
0
0
0

## Slide 37: Goals of PERT Charts
Determination of total project time („project duration“)
Determination of the critical path
Determination of slack times

## Slide 38: Project: Functions, Activities and Tasks
Project
Activity
Activity
Activity
Function
Function
Activity
Activity
Activity
Task
Task
Task
Task
A Project has a duration and consists of functions, activities and tasks
Exercise: Write the corresponding UML class diagram!

## Slide 39: Functions
Definition Function: An activity or set of activities that span the duration of the project

## Slide 40: Functions
Examples:
  Project management
  Configuration Management
  Documentation
  Quality Control (Verification and validation)
  Training
Question: Is system integration a project function?
Mapping of terms: Project Functions in the IEEE 1058 standard are called Integral processes in the IEEE 1074 standard. Sometimes also called cross-development processes

## Slide 41: Tasks
Function
Function
Project
Activity
Task
Activity
Activity
Activity
Activity
Activity
Task
Task
Task
• Smallest unit of work subject to management
• Small enough for adequate planning and tracking
• Large enough to avoid micro management
Notes: Examples of tasks:
  Selection of a database management system (Database)
  Selection of a visualization system (Visualization)
  Selection of a user interface builder (UI)
  Reading the help bulletin board (TA)
  Define documentation and coding standards (Architecture)

## Slide 42: Tasks
Smallest unit of management accountability
  Atomic unit of planning and tracking
  Tasks have finite duration, need resources, produce tangible result (documents, code)
Specification of a task: Work package
  Name, description of work to be done
  Preconditions for starting, duration, required resources
  Work product to be produced, acceptance criteria for it
  Risk involved
Completion criteria
  Includes the acceptance criteria for the work products (deliverables) produced by the task.

## Slide 43: Determining Task Sizes
Finding the appropriate task size is problematic
  Todo lists from previous projects
  During initial planning a task is necessarily large
  You may not know how to decompose the problem into tasks at first
  Each software development activitity identifies more tasks and modifies existing ones
Tasks must be decomposed into sizes that allow monitoring
  Work package usually corresponds to well defined work assignment for one worker for a week or a month.
  Depends on nature of work and how well task is understood.

## Slide 44: Action Item
Definition Action Item: A task assigned to a project participant
  What?, Who?, When?
  Heuristics for Duration: be done within two week or a week
Action items should appear on the meeting agenda in the Status Section
Examples of Todos:
  Unit test class Foo
  Develop project plan.
Example of action items:
  Bob posts the next agenda for the context team meeting before Sep 10, 12 noon.
  The test team develops the test plan by Sep 18

## Slide 45: Activities
Activity
Function
Function
Project
Task
• Major unit of work
with precise dates
• Culminates in project
milestone.
Task
Task
Task
Activity
Activity
Activity
Activity
Activity
• Consists of smaller
activities or tasks

## Slide 46: Activities
Major unit of work
Culminates in major project milestone:
  Internal checkpoint should not be externally visible
  Scheduled event used to measure progress
Milestone often produces project baselines:
  formally reviewed work product
  under change control (change requires formal procedures)
Activitites may be grouped into larger activities:
  Establishes hierarchical structure for project (phase, step, ...)
  Allows separation of concerns
  Precedence relations often exist among activities

## Slide 47: UML Model of Tasks, Activities and Project Functions

## Slide 48: “Laws” of Project Management
Projects progress quickly until they are 90% complete. Then they remain at 90% complete forever.
When things are going well, something will go wrong.
When things just can’t get worse, they will.
When things appear to be going better, you have overlooked something.
If project content is allowed to change freely, the rate of change will exceed the rate of progress.
Project teams detest progress reporting because it manifests their lack of progress.
Notes: The 90% syndrom is a problem that is particularly symptomatic for the linear waterfall lifecycle
Another variant of Murphy's law
Free change problem must be dealt with even in an iterative and incremental software lifecycle: time-boxed prototyping
Introducing new bugs: This is a significant problem in old systems that did not use encapsulation: Global variables, etc
Problem with hierarchical project management

## Slide 49: Summary
Software engineering is a problem solving activity
  Developing quality software for a complex problem within a limited time while things are changing
The system models addresses the technical aspects:
  Object model, functional model, dynamic model
Other models address the management aspects
  WBS, Schedule are examples
  Task models, Issue models, Cost models
Introduction of some technical terms
  Project, Activity, Function, Task, WBS
If this is a 2-semester course:
  We will elaborate on many of these concepts in more detail.

## Slide 50: Backup Slides

## Slide 51: Use These Slides jn a 2 Semester Course

## Slide 52: Software Engineering: A Problem Solving Activity
Analysis: Understand the nature of the problem and break the problem into pieces
Synthesis: Put the pieces together into a large structure
For problem solving we use
  Techniques(Methods): Formal procedures for producing results using some well-defined notation
  Tools: Instrument or automated systems to accomplish a technique
  Methodologies: Collection of techniques applied across software development and unified by a philosophical approach
Where does Management come in? When the available resources to solve the problem are limited (time, people, budget), or if we allow the problem to change.
Notes: What is Software Engineering? The goal is to produce high quality software to satisfy a set of functional and nonfunctional requirements. How do we do that?
First, and foremost, by acknowledging that it is a problem solving activity. That is, it has to rely on well known techniques that are used all over the world for solving problems. There are two major parts of any problem solving process:
Analysis: Understand the nature of the problem. This is done by looking at the problem and trying to see if there are subaspects that can be solved independently from each other. This means, that we need to identify the pieces of the puzzle (In object-oriented development, we will call this object identification).
Synthesis: Once you have identified the pieces, you want to put them back together into a larger structure, usually by keeping some type of structure within the structure.
Techniques, Methodologies and Tools: To aid you in the analysis and synthesis you are using 3 types of weapons: Techniques are well known procedures that you know will produce a result (Algorithms, cook book recipes are examples of techniques). Some people use the word “method” instead of technique, but this word is already reserved in our object-oriented development language, so we won’t use it here. A collection of techniques is called a methodology. (A cookbook is a methodology). A Tool is an instrument that helps you to accomplish a method. Examples of tools are: Pans, pots and stove. Note that these weapons are not enough to make a really good sauce. That is only possible if you are a good cook. In our case, if you are a good software engineer. Techniques, methodologies and tools are the domain of discourse for computer scientists as well. What is the difference?

## Slide 53: Software Engineering: Definition
20
Software Engineering is a collection of techniques,
methodologies and tools that help
with the development of
  a high quality software system
  with a given budget
  before a given deadline
while change occurs.

## Slide 54: Assumptions and Requirements for this Class
Assumption:
  You understand the issues in the analysis or design of a system
  You want to learn more about the managerial aspects of analysis and design of complex software systems
Requirements:
  You have taken Software Engineering I or an equivalent class
Beneficial:
  You have practical experience with maintaining or developing a large software system and have experienced major problems

## Slide 55: Objectives of the Class
Appreciate Software Engineering management
  Manage the construction complex software systems in the context of frequent change
Understand how to
  produce a high quality software system within time
  while dealing with complexity and change
Appreciate that managerial knowledge is needed when developing software system
We assume that you have the technical knowledge

## Slide 56: Required Technical Knowledge
You have taken Software Engineering I or a similar course
You understand the problems of system modeling
You are familiar with UML (Unified Modeling Language)
You are able to apply different modeling methods:
    Use Case modeling
    Object Modeling
    Dynamic Modeling
You are able to use a CASE Tool:
  CASE (Computer Aided Software Engineering)
    Examples: Together-J, Rational Rose
You understand Component-Based Software Engineering
  You are able to use Design Patterns and Frameworks

## Slide 57: What do you learn in this class?
Better understand the Software Lifecycle
  Learn about different software lifecycles
  Greenfield Engineering, Interface Engineering, Reengineering
Learn about the differences between Process vs Product
Learn more about basic project management activities and dealing with resources:
  Schedule: How to map activities into time
  Organization and People: How to set up a project organization
  Cost: How to estimate the cost of a project
Learn how to deal with change and uncertainty
Learn how to set up a project plan, how to control its execution
Learn how to become a leader, how to deal with teams, and make decisions in the context of project management trade-offs
  Cost vs People vs Schedule, Buy vs Build, …

## Slide 58: Management vs Project Mangement
Management is usually defined in terms of functions: planning, organizing, directing, controlling and communicating
  Management is getting things done through people.
Project management is defined in the context of a project
  Project management tries to accomplish a specific task within a time frame and defined resources.
Think about this distinction as we go through the next slides
Notes: Functional requirements for PM (Use cases)
Planning
Organizing
Directing
Controlling
Communicating
Actors: Manager, Developer and Client

## Slide 59: Lecture Schedule
Introduction and Basic Concepts (SPMP, IEEE 1058)
Work Breakdown structures (Decomposition of work)
Scheduling (Project duration, critical path analysis)
Project Organization (Organization forms, team-based projects)
Software Lifecycle (Lifecycle models, IEEE 1074)
Rationale Management (Acquiring and externalizing knowledge, dealing with conflicts and resolutions)
Configuration Management (Dealing with change, SCMP, IEEE 1042)
Methodologies

## Slide 60: Additional Readings
[Kemerer 1997] Software Project Management: Readings and Cases, MacGraw Hill 1997. ISBN: 0-256-18545-X
Frederick Brooks, No Silver Bullet, IEEE Computer, 20, 4 10-19, April 1987, in [Kemerer 1997]
[Royce 1998]Software Project Management: A Unified Framework, Addison Wesley, 1998. ISBN 0-201-30958-0
[IEEE 1997] IEEE Standards Collection Software Engineering. ISBN 1559378980. We will cover the following standards
  [IEEE Std 1058], Software Project Management Plan (SPMP)
  [IEEE Std 828] Software Configuration Management
  [IEEE Std 1042] Guide to Configuration Management Plan (SCMP)
  [IEEE Std 1074] Software Lifecycle Management
  [IEEE Std. 1074.1] Guide to IEEE 1074

## Slide 61: Software Lifecycle
Software lifecycle:
  Set of activities and their relationships to each other to support the development of a software system
Typical lifecycle questions:
  Which activities should I select for the software project?
  What are the dependencies between activities?
  Can I break these activities into more manageable parts?
  How should I schedule the activities?
  How do I assign people to these activities
  How do I control the execution of the activities
  What do I do if the activities are not proceedings as planned?

## Slide 62: Example of Software Lifecycle Activities
Subsystems
Structured By
class...
class...
class...
Source
Code
Implemented
By
Solution Domain
Objects
Realized By
System
Design
Object
Design
Implemen-
tation
Testing
Application
Domain
Objects
Expressed in Terms Of
Test
Cases
?
Verified
By
class....
?
Requirements
Elicitation
Use Case
Model
Analysis

## Slide 63: Standard for modeling lifecycles IEEE Std 1074
The IEEE Std 1074 defines
  The set of activities that constitute mandatory processes for the development and maintenance of software
  Management and support processes through the entire lifecyle
    From concept exploration through retirement
It does not define a software lifecycle on its own
  This must be done by the project manager
  Also called „Tailoring the software lifecycle“

## Slide 64: IEEE Std 1074: Standard for Software Lifecycles
IEEE Std 1074
Project
Management
Pre-
Development
Develop-
ment
Post-
Development
Cross-
Development
(Integral Processes)
> Project Initiation
>Project Monitoring
&Control
> Software Quality
Management
> Concept
Exploration
> System
Allocation
> Requirements
Analysis
> Design
> Implemen-
tation
> Installation
> Operation &
Support
> Maintenance
> Retirement
> V & V
> Configuration
Management
> Documen-
tation
> Training
Process Group
Processes

## Slide 65
Software Lifecycle activities are important abstractions when planning and executing a project
Finding them and managing them will be a recurring topic during the semester
Software life cycle activities are just one type of activity that has to be managed during a project