## Slide 1: 14.2 Work Breakdown Structures
Camp III
Camp II
Camp I

## Slide 2: Outline
In the last lecture we introduced the SPMP
In this lecture we focus on Section 5 of the SPMP
  Developing a Work breakdown structure (WBS)
  Dependencies between tasks
  Scheduling
Notations for visualizing dependencies
Many heuristics and examples
  How detailed should a WBS be?
  How can you plan a long project when things are unknown or changing all the time?

## Slide 3: What is the problem?
Your boss: “How long will this take?”
You: “Between 1 and 6 months.”
People are not happy when you respond that way.
  You figure out that finishing anytime before six months will meet your promise.
  Your boss figures that with some hard work you can be done in a month!
In reality, you don’t have the slightest clue how long it will take, because you don’t know the work to be done.
Solution: Use divide and conquer
  To give a good answer you have to break the work down into activities for which you can get good timing estimates
  From these estimates you compute the estimated project duration

## Slide 4: Activities to obtain good time estimates
Identify the work that needs to be done
  Work breakdown structure (WBS)
Identify the dependency between work units
  Dependency Graph
Estimate the duration of the work to be done
  Schedule

## Slide 5: Software Project Management Plan (IEEE Std 1058)
0. Front Matter
1. Introduction
2. Project Organization
3. Managerial Process
4. Technical Process
5. Work Elements, Schedule, Budget
  5.1 Work Breakdown Structure (WBS)
  5.2 Dependencies between tasks
  5.3 Resource Requirements
  5. 4 Budget
  5.5 Schedule
Optional Inclusions

## Slide 6: (From last lecture) Let‘s Build a House
What are the activities that are needed to build a house?

## Slide 7: 1) Identify the work to be done: Work Breakdown Structure
Surveying
Excavation
Request Permits
Buy Material
Lay foundation
Build Outside Wall
Install Exterior Plumbing
Install Exterior Electrical
Install Interior Plumbing
Install Interior Electrical
Install Wallboard
Paint Interior
Install Interior Doors
Install Floor
Install Roof
Install Exterior Doors
Paint Exterior
Install Exterior Siding
Buy Pizza
Finding these activities is a brainstorming activity.
It is requires similar activities used during requirements engineering
And analysis (use case modeling)

## Slide 8: 2) Hierarchically organize the activities
Building the house consists of
  Prepare the building site
  Building the Exterior
  Building the Interior
Preparing the building site consists of
  Surveying
  Excavation
  Buying of material
  Laying of the foundation
  Requesting permits
Finding this organization involves categorization and refinement. Good
after brainstorming, not during brainstorming

## Slide 9: 3) Identify dependencies between tasks
The work breakdown structure does not show any dependence among the activities/tasks
  Can we excavate before getting the permit?
  How much time does the whole project need if I know the individual times?
    What can be done in parallel?
  Are there any critical actitivites, that can slow down the project significantly?
Dependencies like these are shown in the dependency graph
  Nodes are activities
  Lines represent temporal dependencies

## Slide 10: Building a House (Dependency Graph)
START
Request
Survey
ing
Excava
tion
Buy
Material
Founda
tion
Build
Outside
Wall
Install
Exterior
Plumbing
Install
Interior
Plumbing
Install
Exterior
Electrical
Install
Interior
Electrical
Install
Exterior
Siding
Install
Wallboard
Paint
Exterior
Install
Roofing
Install
Flooring
Paint
Interior
Install
Interior
Doors
Install
Exterior
Doors
FINISH
The activity
„Buy Material“ must
Precede the activity
„Lay foundation“
Lay

## Slide 11: 4) Map tasks onto time
Estimate starting times and durations for each of the activities in the dependency graph
Compute the longest path through the graph: This is the estimated duration of your project

## Slide 12: Building a House (Schedule, PERT Chart)
Duration
Start Time
Slack Time
Each Activity has a start time and an estimated duration
START
8/27/94
0
0
Request
Permits
8/27/94
15
0
Survey
ing
8/27/94
3
12
Excava
tion
9/17/94
10
0
Legend
8/29/94
0
Buy
Material
10/1/94
10
0
Lay
Founda
tion
10/15/94
15
0
Build
Outside
Wall
11/5/94
20
0
Install
Exterior
Plumbing
12/3/94
10
12
Install
Interior
Plumbing
12/3/94
12
0
Install
Exterior
Electrical
12/17/94
10
12
Install
Interior
Electrical
12/21/94
15
0
Install
Exterior
Siding
12/31/94
8
12
Install
Wallboard
1/11/95
9
0
Paint
Exterior
1/12/95
5
12
Install
Roofing
1/19/95
9
12
Install
Flooring
1/22/95
18
0
Paint
Interior
1/22/95
11
0
Install
Interior
Doors
2/8/95
7
0
Install
Exterior
Doors
1/19/95
6
15
FINISH
2/16/95
0
0
0

## Slide 13: How do we get good estimate times?
Estimation of starting times and durations is crucial for setting up a plan.
We will discuss methods and heuristics on how to do it and how to establish a project schedule.
  However, first let us learn a few more technical terms

## Slide 14: Recall SPMP Definitions
Project:
  A Project has a duration and consists of functions, activities and tasks
Work Package:
  A description of the work to be accomplished in an activity or task
Work Product:
  Any tangible item that results from a project function, activity or task.
Project Baseline:
  A work product that has been formally reviewed and agreed upon.
  A project baselines can only be changed through a formal change procedure
Project Deliverable:
  A work product to be delivered to the customer

## Slide 15: Definitions: Functions, Activities and Tasks
Project
Activity
Activity
Activity
Function
Function
Activity
Activity
Activity
Task
Task
Task
Task
A Project has a duration and consists of functions, activities and tasks

## Slide 16: Activities
Activity
Function
Function
Project
Task
• Major unit of work
with precise dates
• Culminates in project
milestone.
Task
Task
Task
Activity
Activity
Activity
Activity
Activity
• Consists of smaller
activities or tasks

## Slide 17: Project Functions
Definition (Project) Function: An activity or set of activities that span the duration of the project

## Slide 18: Project Functions
Examples:
  Project management
  Configuration Management
  Documentation
  Quality Control (Verification and validation)
  Training
Question: Is system integration a project function?
  It Depends…
Mapping of terms: Project Functions in the IEEE 1058 standard are called Integral processes in the IEEE 1074 standard. Sometimes also called cross-development processes

## Slide 19: Tasks
Function
Function
Project
Activity
Task
Activity
Activity
Activity
Activity
Activity
Task
Task
Task
• Smallest unit of work subject to management
• Small enough for adequate planning and tracking
• Large enough to avoid micro management
Notes: Examples of tasks:
  Selection of a database management system (Database)
  Selection of a visualization system (Visualization)
  Selection of a user interface builder (UI)
  Reading the help bulletin board (TA)
  Define documentation and coding standards (Architecture)

## Slide 20: Tasks
Smallest unit of management accountability
  Atomic unit of planning and tracking
  Tasks have finite duration, need resources, produce tangible result (documents, code)
The description of a task is done in a Work package
  Name, description of work to be done
  Preconditions for starting, duration, required resources
    Other Work packages that need to be completed before this task can be started.
  Work product to be produced, acceptance criteria for it
  Risk involved
Completion criteria
  Includes the acceptance criteria for the work products (deliverables) produced by the task.

## Slide 21: Determining Task Sizes
Finding the appropriate task size is problematic
  Todo lists and templates from previous projects
  During initial planning a task is necessarily large
  You may not know how to decompose the problem into tasks at first
  Each software development activitity identifies more tasks and modifies existing ones
Tasks must be decomposed into sizes that allow monitoring
  Depends on nature of work and how well task is understood.
  Work package usually corresponds to well defined work assignment for one worker for a week or two.
  Work assignments are also called action items

## Slide 22: Action Item
Definition Action Item: A task assigned to a person , a a to-do, to be done by a certain time
  What?, Who?, When?
  Heuristics for Duration: be done within one week or two weeks
Action items should be tracked by the project manager
They should appear on the meeting agenda in the Status Section
Examples of Todos:
  Unit test class Foo
  Develop project plan.
Example of an action item:
  Bob posts the next agenda for the context team meeting before Sep 10, 12 noon.
  The test team develops the test plan by Sep 18

## Slide 23: Activities
Major unit of work
Culminates in major project milestone:
  Internal checkpoint should not be externally visible
  Scheduled event used to measure progress
Milestone often produces project baselines:
  formally reviewed work product
  under change control (change requires formal procedures)
Activitites may be grouped into larger activities:
  Establishes hierarchical structure for project (phase, step, ...)
  Activities allow separation of concerns
  Precedence relations often exist among activities

## Slide 24: Developing Work Breakdown Structures
There are several different approaches to develop and display a work breakdown structure. Each is effective under different circumstances
Approaches to break activities into detail by
  Product component approach
    Examples: Design documents, manuals, the running system
  Functional approach
    Analysis, design, implementation, integration, testing, delivery, reviews
  Geographical area
    Examples: TUM team, CMU team, off-shore team, ...
  Organizational approach
    Research, product development, marketing, sales

## Slide 25: When to use what approach
Distributed teams:
  Geographical area approach
Experience d teams:
  Product component approach
Project has mostly beginners or project manager is inexperienced:
  Functional approach
Project is a continuation of previously successful projects, no change in requirements, no new technology
  Organizational approach
When you choose an approach, stick with it to prevent possible overlap in categories

## Slide 26: Mixing different WBS Approaches is bad
Consider the WBS for an activity „Prepare report“
Functional approach:
  Write draft report
  Have draft report reviewed
  Write final report
Product component approach:
  Chapter 1
  Chapter 2
  Chapter 3
Don’t try to mix. Why is this bad?
  Chapter 1
  Chapter 2
  Chapter 3
  Have draft report reviewed
  Write final report
“Prepare the final version of Chapter 3”
can be included in either of the
categories:
“Chapter 3” or “Write final report”

## Slide 27: How do you develop a good WBS?
Top down approach:
  Start at the highest, top level activities and systematically develop increasing levels of detail for all activities.
Brainstorming:
  Generate all activities you can think of that will have to be done and then group them into categories.
Which one you use depends on
  how familiar you and your team are with the project,
  whether similar projects have successfully been performed in the past, and
  how many new methods and technologies will be used.

## Slide 28: The Top Down WBS approach
Specify all activities required for the entire project to be finished
Determine all task required to complete each activity
If necessary specify subactivities required to complete each task
Continue in this way until you have adequately detailed your project.
Approach is good if
  You are or your team is familiar with the problem.
  You have successfully managed a similar project in the past
  You are not introducing new methodologies, methods or tools

## Slide 29: The Brainstorming WBS approach
On a single list, write any activities you think will have to be performed for your project.
Brainstorming means you
  Don’t worry about overlap or level of detail
  Don’t discuss activity wordings or other details
  Don’t make any judgements
  Write everything down
Then study the list and group activities into a few major categories with common characteristics.
If appropriate group activities under a smaller number of tasks
Consider each category you have created and use the top-down WBS approach to determine any additional activities you may have overlooked.

## Slide 30: Displaying Work Breakdown Structures
Three different formats are usually used
Organization-chart format:
  Effectively portrays an overview of your project and the hierarchical relationships of different activities and tasks.
Outline format
  Subactivities and tasks are indented
Bubble format
  The bubble in the center represents your project
  Lines from the center bubble lead to activities
  Lines from activities lead to tasks

## Slide 31
Prepare Report
1.0 Prepare draft report
2.0 Review draft report
3.0 Prepare final report
  3.1 Write final report
  3.2 Print final report
Review
Draft Report
Prepare
Report
Review
Draft Report
Review
Final Report
Print
Final Report
Write
Final Report
Prepare Report
Prepare
Draft Report
Review
Draft Report
Prepare
Final Report
Write
Final Report
Print
Final Report
Org-Chart Format
Outline Format
Bubble Format

## Slide 32: Best format for displaying WBS?
Org-chart format:
  Often good for a “bird view” of the project (executive summaries,...)
  Less effective for displaying large numbers of activities
Outline format:
  Easier to read and understand if WBS contains many activities
Bubble format:
  Effective for supporting the brainstorming process
  Not so good for displaying work breakdown structures to audiences who are not familiar with the project.
  Use bubble format to develop the WBS, then turn it into Org-Chart or outline format.
In large projects:
  Use a combination of org-chart and outline formats:
    Display activities in org-chart format,
    Display subactivities and tasks in outline format.

## Slide 33: Heuristics for developing high quality WBS
Involve the people who will be doing the work in the development of the WBS
  In particular involve the developers
Review and include information from work breakdown structures that were developed for similar projects
  Use a project template if possible
Use more than one WBS approach
  Do project component and functional approach simultaneously
  This allows you often to identify overlooked activities
Make assumptions regarding uncertain activities
  Identify risky activities
  These are often the activities that whose times are hard to estimate
Keep your current work breakdown structure current Update your WBS regularly

## Slide 34: Heuristic: Use Templates
Try to derive the SPMP from a template, either an existing one or one that you start developing with this project.
  A template reflects the cumulative experience gained from doing numerous projects of a particular type.
  Using templates can save you time and improve your accuracy
When developing templates, develop them for frequently performed tasks (reviews, meetings, …). “Checklists”
  Develop and modify your WBS templates from previous projects that worked, not from plans that looked good.
  Use templates as starting points, not as ending points
  Continually update your templates to reflect the experience gained from performing different projects.

## Slide 35: Heuristic: Develop always more than one WBS
Consider to create more several different hierarchies with different categories for your work breakdown structure.
  Having two or more different perspectives helps you identify activities you may overlook.
Good starting point are the following hierarchies:
  Entity-oriented decomposition
  Activity-oriented decomposition
Example: You are running your first object-oriented project.
  Develop a WBS based on the project documents
  Develop a WBS based on the software process activities

## Slide 36: WBS Based on Project Documents (Entity-oriented)
<<Name>>
Project
Problem
Statement
Project
Agreement
RAD
- Write Introduction
- Write Requirements
- Write Constraints
- ...
- Write Introduction
- Describe Functional Model
- Describe Object Model
- Describe Dynamic Model
...
- Write Requirements
- Write Constraints
- Write Acceptance Criteria
- Promise delivery date
SDD
- Write Design Goals
- Write Hardware Software mapping
-Write boundary conditions
- Write Data Management
- Write Open Issues
...

## Slide 37: WBS Based on Software Process (Activity-oriented)
<<Name>>
Project
Project
Initiation
Planning
Analysis
- Establish guidelines
- Formulate requirements with client
- Establish scenarios
- Write project agreement
- Brainstorm on application domain objects
- Develop class diagram
- Partition objects into boundary, entity and control objects
- Develop use cases
- Determine WBS
- Determine dependencies between tasks
- Write SPMP
- Assign teams to subsystems
- Establish project calendar
Design
- Develop Models
- Write code
- Present problems to coach
- Give status reports
- Write RAD
- Write SDD
- Write ODD
Question: Which activities mentioned in the WBS based on Project documents
is left out in the WBS based on Software Process?

## Slide 38: Heuristic: Identifying Risky activities
When you identify activities for a work breakdown structure, you can also identify the risks in your project.
Risks are usually associated with “unknown information”.
Unknown information comes in two flavors
  A known unknown: Information that you don’t have but someone else does.
    Find out who has the information and determine what the information is. (Interviews, Phone calls, tasks analysis)
  An unknown unknown: Information that you don’t have because it does not yet exist.
    Develop contingency plans for each of these risks.
    These contingency plans need be followed when you find out the information does not exist.
Write these risks down in SPMP section 3.3 Risk Management

## Slide 39: Risk Management Examples
Risk: Members in key roles leave the project.
  Contingency Plan?
  Roles are assigned to somebody else. Functionality of the system is renegotiated with the client.
Risk: The project is falling behind schedule.
  Contingency Plan?
  Extra project meetings are scheduled.
Risk: Team 1 cannot provide functions needed by team 2.
  Contingency Plan?
  The liaisons of both teams get together to solve this problem
Risk: The SPOT computer will not be available.
  Contingency Plan?
  We will use an IPAQ instead.

## Slide 40: Risk Management Examples ctd
Risk: The selection of the DBMS takes too much time
  Contingency Plan?
  The Database team uses a bridge pattern and provides a test stub to be used by the other teams for data access while the selection process goes on.
Risk: The customer is not available for discussing and reviewing the user interface during development.
  Contingency Plan?
  Make the design decisions that we feel are appropriate
Risk: No suitable wireless library can be found.
  Contingency Plan?
  The wireless team develops its own library

## Slide 41: Choose a single WBS format
Writing the WBS in different formats is good, because it allows you to identify activities that you may have overlooked
However, after you identify these activities add them to either WBS
Choose a single WBS format to be used in the SPMP and for your project:
  Nothing confuses people fast than trying to use two different work breakdown structures to describe the same project.

## Slide 42: How Detailed should the WBS be?
Sometimes the activities are not clear at all, especially in software projects:
  Unclear requirements and/or changing requirements
  Dependency on technology enablers that appear or are promised to appear after project kickoff
  Simultaneous development of hardware and software (“concurrent engineering”)
A project plan, especially for an innovative software project, should not address details beyond 3 months.
  Even for the first 3 months project activities might not all be detailable, for example when the requirements are unclear or change or introduction of technology enablers is expected.
How should we describe a WBS for a longer project?

## Slide 43: Doing a WBS for Long-Term Projects
When developing a work breakdown structure for a long-term project (longer than 3 months), introduce at least two phases
Phase 1 (3 months): Plan your WBS in detail
  Here list all activities that take two weeks or less to complete
Phase 2, Phase 3, … (n-months) Plan the WBS for these phases in less and less detail
  Here list activities that you estimate will take between one and two months
At the end of phase 1, revise the phase 2 activities to the two week level for the next 3 months.
  Modify any future activities as necessary based on the results of your first three months work.
Continue to revise the SPMP this way throughout the project. (SPMP as an “evolving” document)

## Slide 44: Phases and large Projects
Project-Initiation Phase
Steady State Phase
  Initial Planning phase
Project-Termination Phase

## Slide 45: Project-Initiation Phase
Fred Brooks, The mythical months
Activities
  Meet with client, develop the scenarios (as-is, visionary) for problem statement
  Develop an initial top level design: System as a set of subsystems.
  Establish staffing plan (flat staffing, ramping up)
  Identify human resources: existing employees, new employees.
  Hire team members
  Assign a subsystem to each team. Establish two additional cross-functional teams: Architecture&Documentation.
  Write problem statement (with client and other stake holders, involve project members early)
  Write initial SPMP with WBS, without schedule, without budget.
  Get project plan approved
  Kick project off with 2 documents: Problem statement and SPMP
Duration: About 4 weeks
When?
  Before project kickoff

## Slide 46: Initial Planning Phase
Usually after project kickoff, often called “planning phase”
Activities
  Do innovation management on technology enablers that might influence the design or nonfunctional requirements
  Revise requirements and initial design if necessary
  Revise team structure, reassign team members if necessary
  Revise WBS and dependencies
  Establish cost and scheduling information
  Agree with client on requirements, duration and cost of the project (write this in a “project agreement”, a companion document to the SPMP)
Duration: About 2 weeks time.
When?
  Parallel to “requirements elicitation phase”

## Slide 47: Project-Termination Phase
Do a project-review: “What went right, what went wrong”
  also often called “project post-mortem review”
Based on input from the post-mortem session
  Revise your software process, identify in particular any new activities that happened in the project
  Revise your project kickoff activities
  Revise the SPMP template (to be reused for your next project)

## Slide 48: Where are we?
SPMP IEEE Std 1058
0. Front Matter
1. Introduction
2. Project Organization
3. Managerial Process
4. Technical Process
5. Work Elements, Schedule, Budget
  5.1 Work Breakdown Structure (WBS)
  5.2 Dependencies between tasks
  5.3 Resource Requirements
  5. 4 Budget ( => Lecture on cost estimation)
  5.5 Schedule
Optional Inclusions

## Slide 49: Readings
Literature used for this class
  [IEEE Std 1058] Standard for Software Project Management Plans
  Stanley E Portny, Project Management for Dummies, Hungry Minds, 2001, ISBN 0-7645-5283-X
  [Bruegge-Dutoit 2003], Chapter 11 Project Management

## Slide 50: Summary
Work Breakdown Structure (WBS): Set of activities to do (“use cases”)
Dependency Graph: Identification of dependency relationships between activities identified in the WBS
Schedule: Dependency graph decorated with time estimates for each activity
PERT: One of the first techniques proposed to analyse complex dependency graphs and schedules
Gantt Chart: Notation used to visualize schedule