## Slide 1: Royce’s Methodology
Chapter 16, Royce’ Methodology

## Slide 2: Outline
A Mountaineering Example
Project Context
  Goals, Environment, Methods, Tools, Methodology
Methodology Issues
  Planning, Design Reuse, Modeling, Process, Control&Monitoring, Redefinition
Methodology Spectrum
  Royce’s Methodology based on the unified process
  Extreme Programming
Methodological Heuristics
Methodology Summary

## Slide 3: Royce’s Methodology
Demonstration-based approach.
  Identify performance issues early and assess intermediate artifacts.
Architecture-first approach.
  Focus on critical use cases, architecture decisions, and life-cycle plans before committing resources. Address architecture and plan together.
Iterative life-cycle process.
  Each iteration should focus on a specific risk and move the requirements, the architecture, and the planning in a balanced manner.
Component-based development.
  Minimize human generated lines of code. Use commercial components.
Change management environment.
  Automate change processes to deal with changes introduced by iterations.
Round-trip engineering.
  Use automation couple models and source code, decreasing cost of change.
Objective quality control.
  Use automated metrics and quality indicators to assess progress.
Visual modeling languages.
  Use visual languages to support modeling and documentation.

## Slide 4: How much Planning? (Royce)
The project plan is developed iteratively similar to the software.
The Plan is detailed and refined as the stakeholders increase their knowledge in the application and solution domain.
Planning errors are treated like software defects, the earlier they are resolved, the less impact they have on project success.
Work breakdown structure is organized around software life cycle activities.
  The first level elements in the work breakdown structure represent the life cycle workflows (i.e., management, requirements, design, implementation, assessment, and deployment).
  The second level elements represent phases (i.e., inception, elaboration, construction, and transition).
  The third level elements correspond to artifacts that are produced during the phase.
Estimation:
  Compute the initial estimate with a model, such as COCOMO II
  Refine it with the project manager, developers, and testers.
After each iteration, revise plan and estimate to reflect the performance of the project and to address any planning error.
Notes: Refine it with the project manager, developers, and testers. This enables multiple points of view to be factored into the estimate. Moreover, this also enables the project participant to take ownership of the estimate.

## Slide 5: How much Reuse? (Royce)
Buy versus build decisions are treated as risks that should be confronted early in the life cycle (e.g., in the first iterations of the elaboration phase).
  When components are reused in more than one project, the return on investment can be further increased.
Key priniciple: Minimize the amount of human-generated source code
  Reuse commercial components
  use code generation tools
  Use high-level visual and programming languages.
Reuse is treated as a return on investment decision which decreases development time.
  Mature components and tools also reduce time to repair defects
  Immature components and tools increase quality problems drastically to off-set any economic benefit.

## Slide 6: How much Modeling? (Royce)
Modeling artifacts are based on the activities of the Unified Process
  Management Set:
    Captures the artifacts associated with the planning and monitoring activities.
    Ad hoc notations are used to capture the “contracts” among project participants and other stakeholders.
    Specific artifacts: Problem statement, software process management plan, configuration management plan, and status descriptions.
  Requirements set
    Artifacts describing the visionary scenarios, prototypes for user interfaces and the requirements analysis model.
  Design set
    Description of oftware architecture and interface specifications.
  Implementation set
    Source code, components and executables needed for testing the system.
  Deployment set
    All the deliverables negotiated between the project manager and the client.
    In general it contains the executable code, the user manual and the administrator manual.
Test artifacts are part of each of the above sets.
  The management set includes the test plan and procedures. Test specifications are part of the requirements set.
Notes:   Tests are simply viewed as an integral part of the system and the same tools and techniques are used for developing tests.

## Slide 7: Artifact Road Map (Royce)
The diagram of all artifacts sets generated over the phases of a software system
Notes: The diagram of all artifacts sets generated over the phases of a software system is called the artifact road map.
Figure 16-1 shows an example of an artifact map for managing a large software project according to Royce’s methodology.
The slide shows an example of an artifact road map of work products in a project using the Unified Process as a software life cycle model. The artifacts names are the ones used in the book
Informal releases are shown as hollow triangles, baselined artifacts are shown as solid triangles, dashed lines represent the end of a phase (adapted from [Royse 1998])

## Slide 8: How much Process? (Royce)
Scale (The single most important factor in determining the process).
  Smaller Projects (1-10 participants)
    Require much less management overhead
    Performance depends on technical skills of participant and on the tools.
    Focus on the technical artifacts, few milestones, no formal processes.
  Larger Projects (more than 10 participants)
    Management skills of team leaders becomes primary performance bottleneck.
    Well-defined milestones, focus on change management artifacts.
Stakeholder cohesion.
  Cooperating set of stakeholders: flexible plan, informal agreements.
  Contention among stakeholders: formal agreements, well-defined processes
Process flexibility.
  Rigor of the process definition impacted by rigor of contract.
Process maturity.
  Organizations with mature processes are easier to manage
Architectural risk.
  Demonstrate feasibility of the architecture before full-scale commitment.
Domain experience.
  Domain expertise shorten the earlier phases of the life cycle.
Notes: Royce’s methodology includes heuristics and guidelines for tailoring the life cycle process based on the technical and managerial complexity of the project. Royce considers the following factors when tailoring the process:
  A cooperating set of stakeholders enables a flexible plan and informal agreements. For example, projects with a few stakeholders who share a common goal (e.g., the development of an off-the-shelf product by a start up company) often have cooperating stakeholders. This enables plans and requirements to be refined at the beginning of each iteration. Conversely, contention among stakeholders forces more formal agreements and well-defined processes to achieve consensus. For example, projects accomplished by a consortium of organizations often feature contention sets of stakeholders with conflicting goals. A contention set of stakeholders results in more emphasis on use case modeling and demonstration-based reviews. The assessment workflow becomes critical and review and quality ensuring activities take precedence over other workflows to ensure stakeholder acceptance.

## Slide 9: How much Control? (Royce)
Royce’s methodology focuses on three management metrics and four quality metrics.
Management metrics:
  Work. How many tasks have been completed compared to the plan?
  Costs. How many resources have been consumed compared to the budget?
  Team dynamics. How many participants leave the project prematurely and how many new participants are added?
Quality indicators:
  Change traffic. How many change requests are issued over time?
  Breakage. How much source code is reworked per change?
  Rework. How much effort is needed to implement a change?
  Mean time between failures. How many defects are discovered per hours of testing?
Notes: Change management is critical during an iterative process.
  The change process needs to track changes, from request, to approval, assignment, and implementation. Metrics such as the amount of code that was scraped or reworked and the size of the change are critical to control the overall quality of the system.

## Slide 10: Summary of Royce’s Methodology
Issues | Methods
Planning | Evolutionary WBS Initial model-based estimation of cost and schedule (COCOMO II) Iteration planning, including all stakeholders
Modeling | Critical use cases and driving requirements first Architecture first, UML, Round-trip engineering
Reuse | Buy vs. build decisions during elaboration. Focus on mature components
Process | Scale, Stakeholder cohesion, Process flexibility, Process maturity, Architectural risk, Domain experience
Control | Management indicators (work, cost, team dynamics) Quality indicators (change traffic, breakage, rework, MTBF)

## Slide 11: Backup Slides